## Project Planner
EchoSign Project Planner
[5 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Project Proposal & Scope | 1 | 1 | 1 | 1 | 100%
Requirements Gathering | 1 | 2 | 1 | 1 | 100%
Stakeholder Analysis | 1 | 1 | 2 | 3 | 100%
Literature Review | 2 | 3 | 4 | 6 | 100%
Project Planning & Gantt Chart | 2 | 1 | 4 | 6 | 100%
Risk Assessment & KPIs | 2 | 1 | 4 | 6 | 100%
Dataset Collection | 3 | 3 | 3 | 3 | 100%
Data Cleaning & Preprocessing | 4 | 3 | 5 | 5 | 60%
AI Model Development | 5 | 5 | 5 | 6 | 75%
Model Training & Tuning | 7 | 4 | 6 | 7 | 100%
Model Evaluation & Testing | 9 | 3 | 5 | 8 | 60%
UI/UX Design | 1 | 1 | 1 | 1 | 100%
Mobile App Development | 3 | 3 | 4 | 4 | 50%
Backend / API Development | 7 | 4 | 9 | 1 | 0%
AI Model API Integration | 10 | 2 | 8 | 5 | 1%
Live Camera Recognition | 10 | 3 | 10 | 3 | 0%
Arabic Text Output | 11 | 2 | 11 | 5 | 0%
Error Handling & Permissions | 12 | 2 | 12 | 7 | 0%
End-to-End Testing | 13 | 2 | 12 | 5 | 0%
Performance & Accuracy Testing | 14 | 2 | 14 | 6 | 0%
Bug Fixing & Improvements | 15 | 2 | 14 | 2 | 0%
Documentation | 12 | 4 | 14 | 3 | 0%
User Guide & Screenshots | 15 | 1 | 15 | 8 | 0%
Final Report Preparation | 15 | 2 | 15 | 3 | 0%
Final Presentation Preparation | 16 | 1 | 15 | 5 | 0%
Final Review & Submission | 16 | 1 | 16 | 30 | 0%