Project Planning & Management

Project Proposal

Arabic Sign Language Translator

Objective:

To develop a system that translates Arabic sign language into written Arabic text to help people with hearing and speech impairments communicate more easily with others.

Description:

The project aims to recognize Arabic sign language gestures using computer vision and machine learning techniques. The system will capture hand gestures through a camera, analyze them, and translate the recognized signs into Arabic text. The goal is to make communication more accessible and effective.

Tools & Design:

Jupyter Notebook or Google Colab for model development, a camera for capturing gestures, and a simple user interface for displaying the translated text.

Technologies to Use:

Python, OpenCV, TensorFlow or PyTorch, NumPy, Pandas, and machine learning/deep learning techniques.

Team Members & Responsibilities:

| Amira Sameh Mahmoud Mohamed Khalil ElDeeb | Project documentation, testing coordination, and presentation. |
| --- | --- |
| Mennatullah Hany Mohamed Hassan | Data preprocessing and preparation. |
| Naira Hatem Elsherbiny Eid | Model development and evaluation. |
| Rokaia Ali Bakr El-Gouhari | Dataset collection and organization. |
| Salma Osama Ahmed Kandil | UI/UX design, Flutter Mobile Application, and system integration |

# Week 1: Research, Requirements, and Dataset Preparation

- Rokaia: Research Arabic Sign Language and define the project objectives and requirements.

- Naira: Search for and collect a suitable Arabic Sign Language dataset.

- Amira: Explore the dataset, check image quality, labels, and class distribution.

- Mennatullah: Research suitable machine learning and deep learning models for sign recognition.

- Salma: Review the completed UI/UX design and filters, and plan how the model will integrate with the interface.

Deliverables:

- Defined project objectives and requirements.

- Selected and organized dataset.

- Initial dataset exploration report.

- Proposed machine learning model and technologies.

- Completed UI/UX and filters documented, with an initial integration plan

# Week 2: Data Preprocessing and Initial Model Development

# Amira: Clean and organize the dataset and verify the sign labels.

# Naira: Apply image preprocessing techniques, such as resizing and normalization.

# Rokaia: Split the dataset into training, validation, and testing sets.

# Mennatullah: Build and train the initial machine learning or deep learning model.

# Salma: Convert UI-UX design into a flutter code.

# Deliverables:

# Cleaned and organized dataset.

# Preprocessed images ready for training.

# Training, validation, and testing datasets.

# Initial trained model with preliminary evaluation results.

# UI Flutter Application .

# Week 3: Model Evaluation and Application Integration

# Naira: Evaluate model performance using accuracy, precision, recall, and a confusion matrix where appropriate.

# Rokaia: Analyze prediction errors and help improve the model's performance.

# Amira: Test the model on unseen sign language images or video frames.

# Mennatullah: Integrate the trained model with the user interface and camera input, if supported by the project scope.

# Salma: Test the UI/UX and filters and ensure that the interface displays the predicted Arabic text correctly.

# Deliverables:

# Model evaluation results and performance metrics.

# Improved model based on testing results.

# Initial integration of the model with the interface.

# Tested camera or image input functionality, according to the selected implementation.

# Initial working version of the Arabic Sign Language Translator.

# Week 4: Testing, Refinement, and Final Delivery

# Mennatullah: Perform final tests on the dataset and verify the model's predictions.

# Naira: Fix preprocessing issues and document the final data preparation steps.

# Salma: Finalize the model and record the final evaluation results.

# Amira: Test the complete system, fix integration errors, and improve functionality.

# Rokaia: Prepare the final project report, presentation slides, and system demonstration.

# Deliverables:

# Final tested version of the Arabic Sign Language Translator.

# Final model evaluation report.

# Integrated and tested user interface and filters.

# Complete project documentation and presentation slides.

Risk Assessment & Mitigation Plan

| Risk | Potential Impact | Mitigation |
| --- | --- | --- |
| Limited or imbalanced dataset | May reduce recognition performance. | Review class distribution; use suitable augmentation or seek additional data if permitted. |
| Similar-looking signs or incorrect predictions | May produce incorrect Arabic text. | Analyze misclassified samples and compare suitable model approaches. |
| Slow inference or integration issues | May make the app unresponsive. | Test deployment early, measure inference time, and optimize if needed. |
| Lighting and camera variation | May reduce real-world performance. | Test under varied conditions and document limitations. |
| Schedule delays | May affect prototype completion. | Track tasks weekly, prioritize core features, and reserve time for testing. |

Key Performance Indicators (KPIs)

| KPI | How It Will Be Measured |
| --- | --- |
| Model Accuracy | Percentage of correctly classified test samples. |
| Weighted F1-score | Balance between precision and recall across classes. |
| Inference Time | Time required to produce one prediction. |
| Application Success Rate | Percentage of test attempts completing the recognition flow successfully. |
| Task Completion Rate | Percentage of planned tasks completed by their deadlines. |